## To Do
Story Number | Front | Back | Priority | Assigned To | Comments | Points
ST-0 | As a user who wants to estimate travel time, I need a distance and time calculator so that the user can get to places on time | The user should be able to put in multiple destinations and have the time calculated | 1 | Group | Must do first before the rest are able to be started | 10
ST-1 | As a user that wants certain meal options I want to see resturants and view their information. | Acceptance Critera: The user should be able to see nearby resturants and basic info. | 2 | Group |  | 9
ST-2 | As a user who travels often I would like to be able to control how detailed the zoom and spots on the map are. | Acceptance Critera: The user should be able to zoom and remove information about recomendations | 5 | TBD |  | 3
ST-3 | As a user that wants to see where I have been I need to be able to view something that will show a map of what states I've been to so that I have a visual repepresentation of where I have been to | Acceptance Criteria: The User should be able to click on a tab that shows a map of what states they have been to.The states they have been to are brighter colored than those thay have not. They can toggle each state's "been to" status with toggles. | 8 | TBD |  | 1
ST-4 | As a user who wants to wants to travel, I would like to get updates on the weather as I travel from point A to B so I can potentially avoid areas with harsh weather conditions. | Acceptance Criteria: The user should be able to obtain the weather in and around the location they plan to visit. | 4 | TBD |  | 4
ST-5 | As a user who needs gas on a trip, I would like suggestions on places to find gas. | The user should be able to find gas stations near their route when they select the gas option on the map | 3 | TBD |  | 10
ST-6 | As a user with important documents I need the ability to save my doc- uments and organize them on the app so the user has them ready | The user should be able to upload, view, and re- move documents on the app. | 7 | TBD |  | 1
ST-7 | As a user with multiple trips planned I need the ability to save and see all my trips | The user should be able to see and update any saved trips | 6 | TBD |  | 1
| Front | Back

## Doing
Front | Back

## Done
Front | Back